## Master Tracker
Silver Walks — Auth Flow Cleanup Sprint · Week of 13 April 2026
TOTAL TASKS | 25 | DONE | 0 | IN PROGRESS | 0 | BLOCKED | 0 | COMPLETION RATE | 0% | VERIFIED RATE | 0%
# | Day | Engineer | Pair | Scope | Task | Description | Status | Progress % | Verification Status | Verification % | Notes
1 | Monday | Kester | A | BE | Define error response contract | Agree shape { code, message, field? }. Publish before 11am. | Not Started | 0 | Pending | 0
2 | Monday | Kester | A | BE | Login + password reset audit | List every current error response. Mark generic or leaking internals. | Not Started | 0 | Pending | 0
3 | Monday | Izumi | B | BE | Registration + OTP audit | List every error in nurse and elderly registration flows. | Not Started | 0 | Pending | 0
4 | Monday | Grace | A | FE | Login screen audit | Screenshot every state. List broken breakpoints and missing feedback. | Not Started | 0 | Pending | 0
5 | Monday | Ogo | B | FE | Registration screens audit | Walk both nurse and elderly flows. Screenshot missing states. | Not Started | 0 | Pending | 0
6 | Tuesday | Kester | A | BE | Login error codes | INVALID_CREDENTIALS, ACCOUNT_PENDING, ACCOUNT_DEACTIVATED, EMAIL_NOT_VERIFIED. | Not Started | 0 | Pending | 0
7 | Tuesday | Kester | A | BE | Password reset error codes | RESET_TOKEN_EXPIRED, RESET_TOKEN_INVALID, PASSWORD_TOO_WEAK, PASSWORD_SAME_AS_OLD. | Not Started | 0 | Pending | 0
8 | Tuesday | Izumi | B | BE | Registration error codes | EMAIL_ALREADY_EXISTS, PHONE_ALREADY_EXISTS, INVALID_PHONE_FORMAT, WEAK_PASSWORD. | Not Started | 0 | Pending | 0
9 | Tuesday | Izumi | B | BE | OTP error codes | OTP_EXPIRED, OTP_INVALID, OTP_MAX_ATTEMPTS_REACHED, OTP_ALREADY_USED. | Not Started | 0 | Pending | 0
10 | Tuesday | Grace | A | FE | Build shared auth feedback components | FieldError, FormBanner, LoadingButton, PasswordStrengthMeter. | Not Started | 0 | Pending | 0
11 | Tuesday | Ogo | B | FE | Build shared auth feedback components | Agree component API with Grace before splitting screens. | Not Started | 0 | Pending | 0
12 | Wednesday | Grace | A | FE | Login — loading + error states | Spinner on submit. Inline errors. Banner for account-level errors. | Not Started | 0 | Pending | 0
13 | Wednesday | Grace | A | FE | Login — responsive layout | Fix at 375px, 768px, 1024px. No horizontal overflow. | Not Started | 0 | Pending | 0
14 | Wednesday | Grace | A | FE | OTP screen — full feedback | Countdown, wrong code shake, lock state, resend cooldown. | Not Started | 0 | Pending | 0
15 | Wednesday | Ogo | B | FE | Registration — step progress indicator | Visual stepper for nurse and elderly flows. | Not Started | 0 | Pending | 0
16 | Wednesday | Ogo | B | FE | Registration — field-level error display | Map BE error codes to inline errors. Show on blur + submit. | Not Started | 0 | Pending | 0
17 | Thursday | Grace | A | FE | Password reset flow — all states | Step 1, 2, 3 each with loading, error, success states. | Not Started | 0 | Pending | 0
18 | Thursday | Grace | A | FE | Login — success + redirect polish | Role-based routing: nurse vs elderly vs admin. | Not Started | 0 | Pending | 0
19 | Thursday | Ogo | B | FE | Registration — responsive layout fixes | Fix all breakpoints from Monday audit. | Not Started | 0 | Pending | 0
20 | Thursday | Ogo | B | FE | Registration — success + pending states | Elderly email prompt. Nurse ACCOUNT_PENDING explanation screen. | Not Started | 0 | Pending | 0
21 | Thursday | Izumi | B | BE | Auth error integration tests | One test per error code. Assert HTTP status, code string, message. | Not Started | 0 | Pending | 0
22 | Friday | Kester | A | BE | BE PR review + staging deploy | Review Izumi's codes. Confirm consistent shape. Merge to staging. | Not Started | 0 | Pending | 0
23 | Friday | Izumi | B | BE | Postman collection update | Add example request + expected error for every new error code. | Not Started | 0 | Pending | 0
24 | Friday | Grace | A | FE | Login flow — full walkthrough QA | Test Chrome/Safari/Firefox at 375/768/1440px. Trigger every error state. | Not Started | 0 | Pending | 0
25 | Friday | Ogo | B | FE | Registration flow — full walkthrough QA | Walk nurse + elderly flows all breakpoints. Verify all error codes. | Not Started | 0 | Pending | 0

## Kester
Kester · Pair A — Backend · Auth Flow Sprint
TASKS | 5 | DONE | 0 | COMPLETION RATE | 0% | TASKS DONE % | 0% | VERIFIED RATE | 0%
# | Day | Task | Description | Status | Progress % | Completion Rate % | Verification Status | Verification Rate % | Pair Partner | Notes
1 | Monday | Define error response contract | Agree shape { code, message, field? }. Publish before 11am. | Not Started | 0 | 0 | Pending | 0 | Grace
2 | Monday | Login + password reset audit | List every current error response. Mark generic or leaking internals. | Not Started | 0 | 0 | Pending | 0 | Grace
3 | Tuesday | Login error codes | INVALID_CREDENTIALS, ACCOUNT_PENDING, ACCOUNT_DEACTIVATED, EMAIL_NOT_VERIFIED. | Not Started | 0 | 0 | Pending | 0 | Grace
4 | Tuesday | Password reset error codes | RESET_TOKEN_EXPIRED, RESET_TOKEN_INVALID, PASSWORD_TOO_WEAK, PASSWORD_SAME_AS_OLD. | Not Started | 0 | 0 | Pending | 0 | Grace
5 | Friday | BE PR review + staging deploy | Review Izumi's codes. Confirm consistent shape. Merge to staging. | Not Started | 0 | 0 | Pending | 0 | Grace

## Grace
Grace · Pair A — Frontend · Auth Flow Sprint
TASKS | 8 | DONE | 0 | COMPLETION RATE | 0% | TASKS DONE % | 0% | VERIFIED RATE | 0%
# | Day | Task | Description | Status | Progress % | Completion Rate % | Verification Status | Verification Rate % | Pair Partner | Notes
1 | Monday | Login screen audit | Screenshot every state. List broken breakpoints and missing feedback. | Not Started | 0 | 0 | Pending | 0 | Kester
2 | Tuesday | Build shared auth feedback components | FieldError, FormBanner, LoadingButton, PasswordStrengthMeter. | Not Started | 0 | 0 | Pending | 0 | Kester
3 | Wednesday | Login — loading + error states | Spinner on submit. Inline errors. Banner for account-level errors. | Not Started | 0 | 0 | Pending | 0 | Kester
4 | Wednesday | Login — responsive layout | Fix at 375px, 768px, 1024px. No horizontal overflow. | Not Started | 0 | 0 | Pending | 0 | Kester
5 | Wednesday | OTP screen — full feedback | Countdown, wrong code shake, lock state, resend cooldown. | Not Started | 0 | 0 | Pending | 0 | Kester
6 | Thursday | Password reset flow — all states | Step 1, 2, 3 each with loading, error, success states. | Not Started | 0 | 0 | Pending | 0 | Kester
7 | Thursday | Login — success + redirect polish | Role-based routing: nurse vs elderly vs admin. | Not Started | 0 | 0 | Pending | 0 | Kester
8 | Friday | Login flow — full walkthrough QA | Test Chrome/Safari/Firefox at 375/768/1440px. Trigger every error state. | Not Started | 0 | 0 | Pending | 0 | Kester

## Izumi
Izumi · Pair B — Backend · Auth Flow Sprint
TASKS | 5 | DONE | 0 | COMPLETION RATE | 0% | TASKS DONE % | 0% | VERIFIED RATE | 0%
# | Day | Task | Description | Status | Progress % | Completion Rate % | Verification Status | Verification Rate % | Pair Partner | Notes
1 | Monday | Registration + OTP audit | List every error in nurse and elderly registration flows. | Not Started | 0 | 0 | Pending | 0 | Ogo
2 | Tuesday | Registration error codes | EMAIL_ALREADY_EXISTS, PHONE_ALREADY_EXISTS, INVALID_PHONE_FORMAT, WEAK_PASSWORD. | Not Started | 0 | 0 | Pending | 0 | Ogo
3 | Tuesday | OTP error codes | OTP_EXPIRED, OTP_INVALID, OTP_MAX_ATTEMPTS_REACHED, OTP_ALREADY_USED. | Not Started | 0 | 0 | Pending | 0 | Ogo
4 | Thursday | Auth error integration tests | One test per error code. Assert HTTP status, code string, message. | Not Started | 0 | 0 | Pending | 0 | Ogo
5 | Friday | Postman collection update | Add example request + expected error for every new error code. | Not Started | 0 | 0 | Pending | 0 | Ogo

## Ogo
Ogo · Pair B — Frontend · Auth Flow Sprint
TASKS | 7 | DONE | 0 | COMPLETION RATE | 0% | TASKS DONE % | 0% | VERIFIED RATE | 0%
# | Day | Task | Description | Status | Progress % | Completion Rate % | Verification Status | Verification Rate % | Pair Partner | Notes
1 | Monday | Registration screens audit | Walk both nurse and elderly flows. Screenshot missing states. | Not Started | 0 | 0 | Pending | 0 | Izumi
2 | Tuesday | Build shared auth feedback components | Agree component API with Grace before splitting screens. | Not Started | 0 | 0 | Pending | 0 | Izumi
3 | Wednesday | Registration — step progress indicator | Visual stepper for nurse and elderly flows. | Not Started | 0 | 0 | Pending | 0 | Izumi
4 | Wednesday | Registration — field-level error display | Map BE error codes to inline errors. Show on blur + submit. | Not Started | 0 | 0 | Pending | 0 | Izumi
5 | Thursday | Registration — responsive layout fixes | Fix all breakpoints from Monday audit. | Not Started | 0 | 0 | Pending | 0 | Izumi
6 | Thursday | Registration — success + pending states | Elderly email prompt. Nurse ACCOUNT_PENDING explanation screen. | Not Started | 0 | 0 | Pending | 0 | Izumi
7 | Friday | Registration flow — full walkthrough QA | Walk nurse + elderly flows all breakpoints. Verify all error codes. | Not Started | 0 | 0 | Pending | 0 | Izumi

## Legend
Legend & Guide
Status values
Not Started | Task has not begun
In Progress | Task is actively being worked on
Blocked | Task is blocked — add note in Notes column
Done | Task is complete
Verification values
Pending | Awaiting review
In Review | Under review by pair partner or lead
Approved | Reviewed and signed off
Failed | Review failed — needs rework
Engineer colour coding
Kester | Backend — Pair A (login)
Grace | Frontend — Pair A (login)
Izumi | Backend — Pair B (registration)
Ogo | Frontend — Pair B (registration)
How to use this tracker
1. Each engineer updates their own named sheet daily.
2. Set Status via the dropdown — conditional formatting updates automatically.
3. Set Progress % (0–100) as work advances. 100 = fully done.
4. Pair partner sets Verification Status once they review the work.
5. Set Verification % to reflect how much of the output has been verified.
6. The Master Tracker sheet shows all tasks and live summary totals at the top.
7. Upload this file to Google Sheets — all dropdowns and formulas work natively.